## Sheet1
Task | Status | Priority | Sprint Points | Time Estimate
Executive Summary | Completed | High | 1 | 1 hour
System Diagram | Completed | High | 2 | 2 hour
Personas and User Stories | Completed | High | 3 | 3 hour
Interface Diagram | Completed | High | 4 | 4 hours
Team Roles and Qualifications | Completed | High | 0.5 | 0.5 hours
Development Methodology | Completed | High | 1 | 1 hour
Planned Scope | Completed | High | 1 | 1 hour
Task Breakdown and Scheduling | Completed | High | 4 | 4 hours
References | Completed | High | 0.2 | 0.2 hours
Product Backlog | Completed | High | 5 | 5 hours
Initial Product Burn-down chart | Completed | High | 0.5 | 0.5 hours
Set up the starter front end code and Github repository | Completed | High | 1 | 1 hour
Set up the starter back end code and Github repository | Completed | High | 1 | 1 hour
Design the Landing Page for Self-Service Order | Completed | High | 2 | 1-2 hours
Create the menu page | Completed | Medium | 5 | 3 days
Create a Reusable Menu Item React Component | Completed | Medium | 2 | 1-2 hours
Fetch Menu Item Information from the Backend | Not Started | Medium | 2 | 1-2 hours
Add a Navigation Bar for Customers | Completed | Medium | 2 | 1-2 hours
Backend Should Process Menu Item Requests | Completed | Medium | 2 | 1-2 hours
Create a Reusable Button Component for the Manager Interface | Completed | Medium | 2 | 1-2 hours
Add Role-Specific Navigation Bar for Managers | Not Started | Medium | 2 | 1-2 hours
Create the manager landing page | Completed | Medium | 2 | 1-2 hours
Reuse the Customer Menu Item Component | Completed | Medium | 2 | 1-2 hours
Create a Cashier-Specific Layout | Completed | Medium | 2 | 1-2 hours
Add Role-Specific Navigation Bar for Cashiers | Completed | Medium | 2 | 1-2 hours
Implement Checkout Button (Non-Functional) | Completed | Medium | 2 | 1-2 hours
Deploy the website | Completed | Medium | 1 | 1-2 hours
Deploy the backend API | Completed | High | 1 | 3 hours
Implement Google OAuth for Authentication (Backend) | Not Started | High | 8 | 1-3 days
Add Role-Based Redirect After Login (Backend) | Not Started | High | 2 | 1-2 hours
Add Role-Based Navigation Bar Visibility (Frontend) | Not Started | High | 2 | 1-2 hours
Implement Logout Functionality (Frontend) | Not Started | High | 2 | 1-2 hours
Implement Login Page (Frontend) | Not Started | High | 2 | 1-2 hours
Implement fetch request for the login (Frontend) | Not Started | High | 2 | 1-2 hours
Add Allergen and Nutritional Information to Menu Items | Not Started | Low | 2 | 1-2 hours
Display Allergen Alerts When Selecting Items | Not Started | Low | 2 | 1-2 hours
Create an API endpoint that returns the menu item components with its ingredients | Not Started | High | 3 | 3 hours
Implement Cart Functionality | Not Started | High | 5 | 2 days
Complete ordering functionality | Not Started | Low | 2 | 1-2 hours
Create a Sales Reports Page | Not Started | High | 4 | 3-4 hours
Create Inventory Usage Report | Not Started | High | 4 | 3-4 hours
Integrate Weather API for Manager Landing Page | Not Started | High | 2 | 2 hours
Create Get Inventory API Endpoint | Not Started | High | 4 | 4-5 hours
Create an inventory page that displays all the information of the ingredients | Not Started | Medium | 2 | 1-2 hours
Create Add Inventory API Endpoint | Not Started | High | 2 | 2 hours
Create Edit Inventory API Endpoint | Not Started | High | 2 | 2 hours
Create Frontend Form for Adding/Editing ingredients | Not Started | Medium | 2 | 1-2 hours
Validation and error handling for Add/Edit Inventory | Not Started | High | 8 | 1-3 days
Create Delete Inventory API Endpoint | Not Started | High | 3 | 3 hours
Create Frontend Button for Deleting Ingredients | Not Started | Low | 2 | 1-2 hours
Error Handling for Ingredient Delete Operation | Not Started | Low | 2 | 1-2 hours
Create Admin Page Layout | Not Started | Low | 2 | 1-2 hours
Add Navigation Link to Admin Page in Manager Landing Page | Not Started | High | 1 | 1 hours
Create Add Employee API Endpoint | Not Started | High | 4 | 3-4 hours
Create Edit Employee API Endpoint | Not Started | High | 4 | 3-4 hours
Add Buttons to Trigger Add or Edit Mode | Not Started | Low | 2 | 1-2 hours
Design Unified Edit/Add Employee Form | Not Started | Low | 2 | 1-2 hours
Handle Validation and Error Messaging in the Unified Form | Not Started | Low | 2 | 1-2 hours
Create a landing page for the menu page | Not Started | Low | 2 | 1-2 hours
Design the Menu Items Page Layout | Not Started | Low | 2 | 1-2 hours
Create Add Menu Item API Endpoint | Not Started | High | 4 | 3-4 hours
Create Edit Menu Item API Endpoint | Not Started | High | 4 | 3-4 hours
Create Delete Menu Item API Endpoint | Not Started | High | 4 | 3-4 hours
Implement Menu Item Add/Edit Form with Conditional Logic | Not Started | Low | 2 | 1-2 hours
Add Buttons to Navigate to Menu Item Components | Not Started | Low | 2 | 1-2 hours
Design the Menu Item Components Page Layout | Not Started | Low | 2 | 1-2 hours
Create Add Item Component API Endpoint | Not Started | High | 4 | 3-4 hours
Create Edit Item Component API Endpoint | Not Started | High | 4 | 3-4 hours
Create Delete Item Component API Endpoint | Not Started | High | 4 | 3-4 hours
Implement Item Component Add/Edit Form with Conditional Logic | Not Started | Low | 2 | 1-2 hours
Manage Ingredients within Components | Not Started | Low | 2 | 1-2 hours
Create a Reviews Section in the Menu Item Component | Not Started | Low | 2 | 1-2 hours
Set Up Backend API to Retrieve Reviews | Not Started | High | 5 | 5-4 hours
Create Reviews database table | Not Started | Low | 2 | 1-2 hours
Display Average Rating and Number of Reviews | Not Started | Low | 2 | 1-2 hours
Add a 'Leave a Review' Button to the Menu Item Component | Not Started | Low | 2 | 1-2 hours
Build a Review Submission Form | Not Started | Low | 2 | 1-2 hours
Implement Backend API for Review Submission | Not Started | High | 3 | 1-3 hours
Validate and Display Customer Reviews in Real Time | Not Started | Low | 2 | 1-2 hours
Create a Review Summary Report for Managers | Not Started | High | 5 | 5 hours
Display the Review summary report under Reports Page | Not Started | High | 4 | 4 hours
Implement Frontend Form Validation | Not Started | Low | 2 | 1-2 hours
Set Up Backend Error Handling | Not Started | Low | 2 | 1-2 hours
Integrate Frontend Error Boundaries | Not Started | Low | 2 | 1-2 hours
Automated Testing Suite | Not Started | Low | 2 | 1-2 hours
Create Order History Page | Not Started | High | 8 | 1 day
Develop Backend API to Fetch Order History | Not Started | High | 4 | 3-4 hours
Design Order Summary Cards or Table | Not Started | High | 4 | 3-4 hours
Implement Search and Filter Functionality | Not Started | Low | 2 | 1-2 hours
Error Handling and Loading States | Not Started | Low | 2 | 1-2 hours
Integrate Google Translate API into the kiosk interface | Not Started | High | 4 | 3-4 hours
Create a dropdown menu on the main screen for language selection | Not Started | Low | 2 | 1-2 hours
Ensure all menu text, buttons, and labels dynamically update when a language is selected | Not Started | Low | 2 | 1-2 hours
Design icons and buttons with a larger-than-standard size | Not Started | Low | 2 | 1-2 hours
Use universally recognized symbols for actions | Not Started | Low | 2 | 1-2 hours
Develop a toggle switch on the main screen to enable high-contrast mode | Not Started | Low | 2 | 1-2 hours
Create a separate high-contrast color scheme | Not Started | Low | 2 | 1-2 hours
Ensure that all images, text, and icons adjust to the high-contrast setting | Not Started | Low | 2 | 1-2 hours
Add a text resizing feature on the main screen | Not Started | Low | 2 | 1-2 hours
Ensure that resized text adapts fluidly across all layouts | Not Started | Low | 2 | 1-2 hours
Test functionality with screen magnifiers | Not Started | Low | 2 | 1-2 hours
Provide a 'Text Size' button directly on each page | Not Started | Medium | 5 | 4-6 hours
Implement large, readable text settings | Not Started | Low | 2 | 1-2 hours
Add descriptive alt text to each image and icon | Not Started | Low | 2 | 1-2 hours
Verify screen reader compatibility | Not Started | Low | 2 | 1-2 hours
Integrate a text-to-speech (TTS) option | Not Started | Low | 2 | 1-2 hours
Add a 'Read Aloud' button next to each main section | Not Started | Low | 2 | 1-2 hours
Ensure universal icons and symbols are easily understood | Not Started | Low | 2 | 1-2 hours
Design a streamlined layout with minimal elements per page | Not Started | Low | 2 | 1-2 hours
Group related items for clarity | Not Started | Low | 2 | 1-2 hours
Design Display-Only Interface Layout for Multi-Display | Not Started | Low | 2 | 1-2 hours
Develop a Responsive Layout to Adapt to Large Screens | Not Started | Low | 2 | 1-2 hours
Implement Auto-Scroll or Slide Features | Not Started | Low | 2 | 1-2 hours
Configure Backend for Real-Time Updates | Not Started | Low | 2 | 1-2 hours
Ensure Consistency of Displayed Menu and Promotional Information | Not Started | Low | 2 | 1-2 hours
291.2